## Latihan
COST BENEFIT ANALYSIS
| 2011 | 2012 | 2013 | 2014 | 2015
| Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Discount rate (%) (usually between 3-10%) | 3%
Discount factor (1/(1+discount rate)^n)
Complaint Management Systems Development Project
Item | 2011 | 2012 | 2013 | 2014 | 2015
| Year 1 | Year 2 | Year 3 | Year 4 | Year 5
BENEFIT ANALYSIS
Increased sales | 500000 | 530000 | 561800 | 595508 | 631238
Reduction in customer complaint calls | 70000 | 70000 | 70000 | 70000 | 70000
Reduced inventory costs | 68000 | 68000 | 68000 | 68000 | 68000
TOTAL BENEFITS
PV OF BENEFITS
PV OF ALL BENEFITS
COST ANALYSIS
2 Servers @125000 | 250000 | 0 | 0 | 0 | 0
Printer | 100000 | 0 | 0 | 0 | 0
Software Licenses | 34825 | 0 | 0 | 0 | 0
Server software | 10945 | 0 | 0 | 0 | 0
Development labor | 1236525 | 0 | 0 | 0 | 0
TOTAL DEVELOPMENT COST
Hardware | 54000 | 81261 | 81261 | 81261 | 81261
Software | 20000 | 20000 | 20000 | 20000 | 20000
Operational Labor | 111788 | 116260 | 120910 | 125746 | 130776
TOTAL OPERATIONAL COSTS
TOTAL COSTS
PV OF COSTS
PV OF ALL COST
TOTAL (Benefit-Cost)
YEARLY NPV
CUMULATIVE NPV
ROI ((total benefit-total cost)/total cost)
BREAK-EVEN POINT |  | years
INTANGIBLE BENEFIT
Note on E35: NURFIT: nilai cumulative benefit-cost sudah positive

## Sheet1
COST BENEFIT ANALYSIS
| 2011 | 2012 | 2013 | 2014 | 2015
| Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Discount rate (%) (usually between 3-10%) | 3%
Discount factor (1/(1+discount rate)^n) | 0.97087 | 0.9426 | 0.91514 | 0.88849 | 0.86261
Complaint Management Systems Development Project
Item | 2011 | 2012 | 2013 | 2014 | 2015
| Year 1 | Year 2 | Year 3 | Year 4 | Year 5
BENEFIT ANALYSIS
Increased sales | 500000 | 530000 | 561800 | 595508 | 631238
Reduction in customer complaint calls | 70000 | 70000 | 70000 | 70000 | 70000
Reduced inventory costs | 68000 | 68000 | 68000 | 68000 | 68000
TOTAL BENEFITS | 638000 | 668000 | 699800 | 733508 | 769238
PV OF BENEFITS | 619417.4757 | 629654.0673 | 640416.1332 | 651712.3575 | 663551.4561 | 3204751.4899
PV OF ALL BENEFITS | 619417.4757 | 1249071.543 | 1889487.6762 | 2541200.0338 | 3204751.4899
COST ANALYSIS
2 Servers @125000 | 250000 | 0 | 0 | 0 | 0
Printer | 100000 | 0 | 0 | 0 | 0
Software Licenses | 34825 | 0 | 0 | 0 | 0
Server software | 10945 | 0 | 0 | 0 | 0
Development labor | 1236525 | 0 | 0 | 0 | 0
TOTAL DEVELOPMENT COST | 1632295 | 0 | 0 | 0 | 0
Hardware | 54000 | 81261 | 81261 | 81261 | 81261
Software | 20000 | 20000 | 20000 | 20000 | 20000
Operational Labor | 111788 | 116260 | 120910 | 125746 | 130776
TOTAL OPERATIONAL COSTS | 185788 | 217521 | 222171 | 227007 | 232037
TOTAL COSTS | 1818083 | 217521 | 222171 | 227007 | 232037
PV OF COSTS | 1765129.1262 | 205034.4048 | 203317.9376 | 201692.7793 | 200157.1545 | 2575331.4024
PV OF ALL COST | 1765129.1262 | 1970163.531 | 2173481.4686 | 2375174.2479 | 2575331.4024
TOTAL (Benefit-Cost) | -1180083 | 450479 | 477629 | 506501 | 537201
YEARLY NPV | -1145711.6505 | 424619.6626 | 437098.1956 | 450019.5783 | 463394.3016 | 629420.0875
CUMULATIVE NPV | -1145711.6505 | -721091.9879 | -283993.7923 | 166025.7859 | 629420.0875 | 629420.0875
ROI ((total benefit-total cost)/total cost) | 24.44% | (629,420/2,575,331)
BREAK-EVEN POINT | 3.6311 | years | [break-even occurs in year 4; (450,019 - 166,026)/450,019 = 0.63)
INTANGIBLE BENEFIT | This service is currently provided by competitors
Improved customer satisfaction
Note on E35: NURFIT: nilai cumulative benefit-cost sudah positive

## Copy-cek (hidden)
COST BENEFIT ANALYSIS
| 2011 | 2012 | 2013 | 2014 | 2015
| Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Discount rate (%) (between 3-10%) | 3%
Discount factor (1/(1+discount rate)^n | 0.97087 | 0.9426 | 0.91514 | 0.88849 | 0.86261
Complaint Management Systems Development Project
Item | 2011 | 2012 | 2013 | 2014 | 2015
| Year 1 | Year 2 | Year 3 | Year 4 | Year 5
BENEFIT ANALYSIS
Increased sales | 500000 | 530000 | 561800 | 595508 | 631238
Reduction in customer complaint calls | 70000 | 70000 | 70000 | 70000 | 70000
Reduced inventory costs | 68000 | 68000 | 68000 | 68000 | 68000
TOTAL BENEFITS | 638000 | 668000 | 699800 | 733508 | 769238
PV OF BENEFITS | 619417 | 629654 | 640416 | 651712 | 663552 | 3204752
PV OF ALL BENEFITS | 619417 | 1249072 | 1889488 | 2541200 | 3204752
COST ANALYSIS
2 Servers @125000 | 250000 | 0 | 0 | 0 | 0
Printer | 100000 | 0 | 0 | 0 | 0
Software Licenses | 34825 | 0 | 0 | 0 | 0
Server software | 10945 | 0 | 0 | 0 | 0
Development labor | 1236525 | 0 | 0 | 0 | 0
TOTAL DEVELOPMENT COST | 1632295 | 0 | 0 | 0 | 0
Hardware | 54000 | 81261 | 81261 | 81261 | 81261
Software | 20000 | 20000 | 20000 | 20000 | 20000
Operational Labor | 111788 | 116260 | 120910 | 125746 | 130776
TOTAL OPERATIONAL COSTS | 185788 | 217521 | 222171 | 227007 | 232037
TOTAL COSTS | 1818083 | 217521 | 222171 | 227007 | 232037
PV OF COSTS | 1765129 | 205034 | 203318 | 201693 | 200157 | 2575331
PV OF ALL COST | 1765129 | 1970163 | 2173481 | 2375174 | 2575331
TOTAL | -1180083 | 450479 | 477629 | 506501 | 537201
YEARLY NPV | -1145712 | 424620 | 437098 | 450019 | 463395 | 629421
CUMULATIVE NPV | -1145712 | -721091 | -283993 | 166026 | 629421
ROI | 24.44% | (629,421/2,575,331)
BREAK-EVEN POINT | 3.63 | years | [break-even occurs in year 4; (450,019 - 166,026)/450,019 = 0.63)
INTANGIBLE BENEFIT | This service is currently provided by competitors
Improved customer satisfaction